TravelCRMPlus

ZNICRM Feature-Parity

Execution Plan

Draft v1 — 2026-05-12

# 1. Executive Summary

ZNICRM offers a tiered SaaS CRM (Free → Starter ₹249 → Grow ₹499 → Scale ₹750 → Business ₹1,250 → Unlimited ₹14,999/mo) with about 80 distinct features spanning lead capture, multi-channel communication, pipeline automation, invoicing, ticketing, inventory, AI, and a website widget.

TravelCRMPlus already has a strong multi-tenant foundation with ~31 implemented modules covering identity, platform admin, tenant settings, leads, tasks, reminders, and inventory primitives. The remaining work is building the customer-facing CRM surface, communication channels, automation engine, and SaaS billing/feature-gating — all on top of the existing infrastructure.

Estimated total scope: 14 phases over 12–18 months with a 3–5 engineer team. The plan is structured so each phase ships a coherent, sellable slice — early phases unlock a working Starter-equivalent plan; the final phases reach Business Suite parity.

# 2. Current TravelCRM Architecture Snapshot

Strengths to build on (not re-build). The infra is production-grade.

| Area | Status |
| --- | --- |
| Auth & Identity | Login, JWT refresh, forgot/reset password, users, roles, departments, permissions catalogue — FULL |
| Platform Admin | Tenant CRUD, dashboard, brand, configs, data reset — FULL |
| Tenant Settings | Brand, system, invoice, SMTP, WhatsApp (Wati), file storage (local + S3), AI provider, locale, scheduled tasks, task types — FULL |
| CRM (existing) | Leads, Tasks, Time Entries, Reminders — FULL. Companies/Customers/Bookings/Packages/Destinations/Pipeline/Reports — frontend stubs |
| Inventory Foundation | Suppliers FULL; Resources / Calendar / Holds backend complete; pricing strategy hook |
| Cross-cutting | Multi-tenancy (subdomain or header), JWT, API envelope, FluentValidation + MediatR, audit logging, correlation ID, Hangfire (heartbeat / overdue / hold-expiry), Serilog → console+file+Seq, PostgreSQL/EF Core |

## Why this plan stays small

- No need to rebuild infra — auth, tenancy, audit, jobs, storage are production-grade.

- AI provider configs already exist (Anthropic + others) — every AI feature can land without new config plumbing.

- WhatsApp (Wati) is already wired — engagement layer just needs UI + campaign engine on top.

- Hangfire already runs recurring jobs — automation rules use the same scheduler.

- Biggest greenfield areas: Deals/Pipeline, Quotes/Invoices, Campaign engine, Workflow automation, Website widget, AI agents, SaaS billing layer.

# 3. ZNICRM Feature Catalogue — Gap Analysis

Each ZNICRM feature mapped against the current TravelCRM state. Present = fully implemented; Partial = infrastructure exists, feature layer missing; Missing = not started.

## 3.1 Lead Management & Capture

| ZNICRM Feature | Status | Notes |
| --- | --- | --- |
| Leads CRUD | Present | Features/Leads + UI |
| Lead Distribution (auto-assign) | Missing | Rule engine: round-robin, region, source, load |
| Facebook Lead Ads → CRM | Missing | OAuth + webhook handler |
| Google Ads form submissions | Missing | Conversion API + form handler |
| IndiaMART feed | Missing | Polling integration |
| TradeIndia feed | Missing | Polling integration |
| WhatsApp inbound → lead | Partial | Wati configured; need inbound webhook |
| Web forms (Universal Contact Forms) | Missing | Form builder + embed snippet |
| Personal / Team Contact Forms | Missing | Permission-scoped form ownership |

## 3.2 Communication & Engagement

| ZNICRM Feature | Status | Notes |
| --- | --- | --- |
| SMS Campaign / Bulk SMS | Missing | SMS provider abstraction (Twilio, MSG91, Gupshup) |
| Email Campaigns | Partial | SMTP available; need campaign builder + audience |
| WhatsApp Bulk Campaigning | Partial | Wati available; need template bulk send |
| Custom Gateways (Email/SMS) | Missing | Provider strategy pattern |
| WhatsApp 1-to-1 Chat | Missing | Conversation thread UI |
| Chat-Bots | Partial | AI provider available; need flow designer |
| Call Sync (Android) | Missing | Mobile app + sync API |
| Call Recording auto-upload | Missing | Mobile app + storage hook |
| Cloud Telephony | Missing | Twilio/Exotel/Knowlarity/Tata Tele adapter |
| Dialer System (click-to-call, auto) | Missing | Browser softphone or telephony bridge |

## 3.3 Sales Pipeline & Deals

| ZNICRM Feature | Status | Notes |
| --- | --- | --- |
| Deals + pipeline stages | Partial | UI stub exists, no entity |
| Proposals / Quotations | Missing | Line items, totals, PDF |
| Pipeline kanban view | Partial | Kanban component exists in theme |
| Followup Intelligence (AI) | Missing | Scoring + recommended next action |
| Deal Revival (AI) | Missing | Stale deal scoring + nudge |
| Checklists (per stage) | Missing | Stage-template checklist engine |

## 3.4 Workflow & Automation

| ZNICRM Feature | Status | Notes |
| --- | --- | --- |
| Workflow Rules | Missing | Trigger → condition → action engine |
| Marketing Automation Rules | Missing | Time + event-based triggers |
| Assignments (rule-based) | Missing | Distinct from one-off assignment |
| Escalations (time-based) | Missing | SLA timers + recipient ladder |
| Approvals (multi-step) | Missing | Approval chain + delegation |

## 3.5 Invoicing & Billing

| ZNICRM Feature | Status | Notes |
| --- | --- | --- |
| Invoice settings | Present | Features/Settings/Invoice |
| Quotes | Missing | Entity + PDF + convert-to-invoice |
| Invoices | Missing | Entity + PDF + payment tracking |
| Multiple Taxes | Missing | Tax catalogue + line-item tax |
| Auto Tax Application (geo) | Missing | Region → tax rule mapping |
| Receipts | Missing | Payment record + email |
| Payment Gateway Integration | Missing | Razorpay / Stripe / PayU adapter |
| Subscriptions (recurring billing) | Missing | Recurring schedule + auto-invoice |

## 3.6 Inventory & Products

| ZNICRM Feature | Status | Notes |
| --- | --- | --- |
| Manage Products (categories + items) | Partial | TravelCRM has travel inventory; generic SKU missing |
| Manage Stocks | Partial | Holds/Calendar exist for travel |
| Vendor Management | Present | Suppliers covers it |
| Purchase Orders | Missing | PO lifecycle entity |

## 3.7 Ticketing / Helpdesk

| ZNICRM Feature | Status | Notes |
| --- | --- | --- |
| Support Panel (customer portal) | Missing | Public-facing ticket creation |
| Email-to-Ticket | Missing | IMAP parser → ticket |
| Knowledge Base | Missing | Articles + search + public site |
| Custom Domain for support | Missing | Wildcard DNS + cert automation |

## 3.8 Integrations

| ZNICRM Feature | Status | Notes |
| --- | --- | --- |
| Zapier / Integrately | Missing | Outbound webhooks + Zapier app |
| Facebook Ads OAuth | Missing | Token storage + webhook |
| Google Ads OAuth | Missing | Token + Conversion API |
| Shopify | Missing | Webhook + cart sync |
| Webhooks (outbound) | Missing | Subscriber model + retry |
| Custom Integration framework | Missing | Plug-in pattern |

## 3.9 ZNIEngage (Website widget)

| ZNICRM Feature | Status | Notes |
| --- | --- | --- |
| Embeddable JS widget | Missing | Standalone Web Component bundle |
| Auto Pop-up Contact Form | Missing | Widget feature |
| Splash Image / Exit Intent / Deal Bar | Missing | Widget feature |
| Cookie Notification | Missing | Widget feature |
| Visit tracking (Monthly Hits) | Missing | Analytics ingest |

## 3.10 AI Features

| ZNICRM Feature | Status | Notes |
| --- | --- | --- |
| AI Credits system | Missing | Token metering + wallet |
| AI Chatbot for Website | Partial | AI provider exists; need chat flow engine |
| WhatsApp AI Chatbot | Partial | Wati + AI provider; need orchestration |
| Followup Intelligence | Missing | Lead-scoring model + UI surface |
| Deal Revival | Missing | Stale-deal detection + revival prompts |

## 3.11 Reporting & Analytics

| ZNICRM Feature | Status | Notes |
| --- | --- | --- |
| Custom Reports builder | Partial | UI stub at pages/crm/reports |
| Manager dashboards | Missing | Per-role aggregated views |
| Standard reports (conversion, ROI, velocity) | Missing | Pre-canned report library |

## 3.12 SaaS Billing & Plan Gating

| ZNICRM Feature | Status | Notes |
| --- | --- | --- |
| Plan tiers (Free/Starter/Grow/Scale/Business/Unlimited) | Partial | Plans concept exists in Platform Admin |
| Feature gating per plan | Missing | Feature-flag map + middleware |
| Per-user seat limits | Missing | Enforce at user creation |
| Document storage quota | Missing | Per-tenant byte counter |
| Rule-count limits | Missing | Webhooks/workflow caps |
| Trial period | Missing | 30-day trial with expiry |
| Billing portal | Missing | Self-serve plan management |

# 4. Multi-Tenancy Strategy

TravelCRM already enforces multi-tenancy via ITenantContext resolved from subdomain or header, with global EF query filters scoping every DbSet. New features extend this in three ways:

4.1 Tenant-Scoped Data

Every new entity (Deal, Quote, Invoice, Campaign, WorkflowRule, Webhook, KnowledgeArticle, Ticket, etc.) must:

- Inherit ITenantOwned (or have a TenantId FK)

- Be covered by the global query filter

- Be audited via AuditSaveChangesInterceptor

4.2 Plan-Gated Features (NEW infrastructure)

A new Features/Subscriptions module to track per-tenant entitlements: TenantSubscription with TenantId, PlanCode (free|starter|grow|scale|business|unlimited), Status (trial|active|past_due|cancelled), TrialEndsAt, CurrentPeriodEnd, SeatLimit, StorageGbLimit, WebhookLimit, WorkflowRuleLimit, …

A [RequiresFeature("WhatsAppBulkCampaign")] attribute on controllers + an IFeatureGate service resolves the tenant's plan → returns 402 Payment Required if not entitled.

4.3 Per-Tenant Resource Limits

Quotas are enforced at two layers:

- Soft (UI) — Angular reads /api/me/entitlements and disables the "Create" button + shows upgrade nudge when the limit is reached.

- Hard (API) — Every Create command in MediatR validation checks the live count against the entitlement; rejects with a clear "limit reached" error before persisting.

4.4 Tenant Provisioning Lifecycle

- 1. Create Tenant row.

- 2. Create TenantSubscription with Status=trial, PlanCode=starter (or free), TrialEndsAt=now+30d.

- 3. Seed the tenant's default workspace (default roles, default pipeline, default task types).

- 4. Hangfire job nightly: scan for trials ending in 3 days → send reminder email; on expiry → flip to past_due, suspend write access.

4.5 Custom Domain per Tenant (Business Suite)

- Wildcard DNS at the load balancer (*.travelcrm.app) — already works for subdomains.

- Custom-domain support (e.g., crm.acme.com) requires: TenantDomain table mapping host → TenantId, Let's Encrypt cert automation, update TenantResolutionMiddleware to check TenantDomain table on cache-miss.

# 5. Proposed Plan Tiers for TravelCRM

6 tiers mirroring ZNICRM, adapted for the travel-vertical. Each feature has a minimum tier; the FeatureGate service holds the mapping.

| Tier | Price (annual) | Storage | Headline features |
| --- | --- | --- | --- |
|  | ₹0 | 1 GB | Lead capture, contacts, basic pipeline, max 3 users |
|  | ₹249/user | 1 GB | + Lead source integrations, call sync, deals, proposals |
|  | ₹499/user | 5 GB | + Web/WhatsApp capture, bulk campaigns, workflows, quotes/invoices, checklists |
|  | ₹750/user | 10 GB | + Helpdesk, follow-up intelligence, dialer, deal revival, advanced automation |
|  | ₹1,250/user | 25 GB | + Approvals, escalations, custom domain, field-team visibility (50 users) |
|  | ₹14,999/mo | Unlimited | All Business features + dedicated support |

# 6. Phased Execution Roadmap

14 phases, each shipping a sellable increment. Effort in story points (1 SP ≈ 1 engineer-day). With 3 engineers in parallel, realistic ship: 12–14 months; with 5 engineers, 9–11 months.

| Phase | Duration | Story Points | Sellable Increment |
| --- | --- | --- | --- |
|  | 2–3 wk | 15 SP | Foundation |
|  | 3–4 wk | 25 SP | Starter MVP |
|  | 2–3 wk | 15 SP | Starter complete |
|  | 3–4 wk | 30 SP | Grow blocks unlock |
|  | 3–4 wk | 35 SP | Starter parity with ZNICRM |
|  | 4–5 wk | 50 SP | Grow parity |
|  | 4–5 wk | 45 SP | Grow complete |
|  | 4–6 wk | 60 SP | Grow / Scale unlock |
|  | 2–3 wk | 25 SP | Business unlock |
|  | 4–6 wk | 50 SP | Scale parity |
|  | 4–5 wk | 50 SP | Scale parity |
|  | 2–3 wk | 20 SP | Cross-tier |
|  | 5–7 wk | 70 SP | Scale / Business |
|  | 3–4 wk | 30 SP | All tiers |
|  | 2–3 wk | 25 SP | Business complete |

# 7. Phase Details

Each phase below specifies the backend, frontend, multi-tenant impact, and effort.

## Phase 0 — Subscriptions, Plans & Feature Gating (2–3 weeks)

Why now: Every later phase reads IFeatureGate.IsEntitled(feature). Building this last would force a retrofit across all phases.

Backend

- Features/Subscriptions/ MediatR module: Plan entity, TenantSubscription entity, FeatureGate service

- [RequiresFeature] action filter — 402 Payment Required if not entitled

- Seed the 6 plans with feature-to-plan mapping (config-driven)

- Trial-expiry Hangfire job (nightly): downgrade to past_due on expiry

- Migration: add seat_limit, storage_used_bytes columns to tenants

Frontend

- pages/platform-admin/plans/ — Platform Admin CRUD for plans + feature toggles

- pages/settings/subscription/ — Tenant Admin view of plan + upgrade button + usage meters

- core/services/entitlements.service.ts — caches /api/me/entitlements

- *hasFeature structural directive for UI feature gating

Multi-tenant impact

Existing features (Leads, Tasks, Reminders, Suppliers) get featureCode = "core_crm" and are entitled in every plan.

Effort: 15 SP

## Phase 1 — Deals & Pipeline (3–4 weeks)

Why now: Pipeline is the heart of every CRM. ZNICRM's USP is "execution-focused" — this is it.

Backend

- Deal entity (lead FK, customer FK, stage, value, currency, expected close, owner)

- PipelineStage per-tenant configurable list

- deals/{id}/move endpoint with stage-change audit

- DealActivity log

Frontend

- pages/crm/pipeline/ — kanban board (drag stage), filter by owner/stage

- pages/crm/deals/ — list + detail (replaces stub)

- Deal-from-Lead conversion flow

Multi-tenant impact

Pipeline stages are per-tenant configurable; standard tenant scoping.

Effort: 25 SP

## Phase 2 — Companies, Customers, Contacts (2–3 weeks)

Why now: Deals need a customer record. Both are currently frontend stubs.

Backend

- Company entity (name, industry, size, address)

- Customer (contact) entity (name, email, phone, company FK, owner)

- Lead-to-customer conversion endpoint

- Dedupe by email/phone

Frontend

- Wire up pages/crm/companies/ and pages/crm/customers/

- Inline create-company from customer form

Multi-tenant impact

Standard tenant scoping.

Effort: 15 SP

## Phase 3 — Quotes & Invoices (3–4 weeks)

Backend

- Quote entity (line items, discount, tax, total, status, valid-until)

- Invoice entity (line items, tax breakdown, paid amount, status)

- TaxRule entity (rate, jurisdiction, applies to product category)

- PDF generation via QuestPDF

- Email-quote / email-invoice via existing SMTP

- Convert-quote-to-invoice flow

Frontend

- pages/crm/quotes/ + pages/crm/invoices/

- PDF preview pane

- Settings → Tax rules CRUD

Multi-tenant impact

TaxRule tenant-scoped; PDF templates use existing tenant brand settings.

Effort: 30 SP

## Phase 4 — Lead Source Integrations (3–4 weeks)

Backend

- LeadSource entity (channel, credentials, last sync)

- Adapter pattern: Facebook Lead Ads (webhook), Google Ads (Conversion API), IndiaMART (poll), TradeIndia (poll), Wati inbound

- Hangfire job per polling adapter

- Webhook endpoint /api/lead-sources/webhook/{channel} with HMAC verification

Frontend

- pages/settings/lead-sources/ — connect/disconnect each channel, OAuth flows

- Lead detail shows source + raw payload

Multi-tenant impact

Plan gating: Starter = manual only; Grow+ = Web + WhatsApp; Business = all sources.

Effort: 35 SP

## Phase 5 — Universal Contact Forms + Website Widget (4–5 weeks)

Why now: ZNIEngage equivalent — standalone embeddable widget separate from the main app.

Backend

- ContactForm entity (fields JSON schema, redirect URL, captcha config)

- FormSubmission entity → auto-creates a Lead

- WidgetSession (anonymous visitor) tracked by cookie

- Public endpoint /public/widget/{publicKey}/submit (rate-limited)

Frontend

- NEW separate Angular sub-app at widget/ → single widget.js (≤60 KB gzipped)

- Web Components: <znw-form>, <znw-popup>, <znw-deal-bar>, <znw-splash>, <znw-exit-intent>, <znw-cookie-banner>

- pages/settings/forms/ — form builder

- pages/settings/widget/ — toggle features, copy embed snippet

Multi-tenant impact

All widget features Grow+; analytics gated by Monthly Unique Hits (10K Starter → 1M Business).

Effort: 50 SP

## Phase 6 — Campaign Engine (Email + SMS + WhatsApp Bulk) (4–5 weeks)

Backend

- Campaign entity (channel, audience segment, template, schedule, status)

- CampaignRecipient (per-customer send state)

- Audience query DSL → JSONLogic compiled to LINQ

- MessageTemplate (channel-specific; WhatsApp uses approved Wati templates)

- Channel adapters: EmailSender (SMTP), SmsSender (Twilio/MSG91/Gupshup), WhatsAppSender (Wati)

- Hangfire fan-out: 1 campaign → N rate-limited send jobs

Frontend

- pages/crm/campaigns/ — campaign builder (audience filter, template, schedule)

- Real-time delivery dashboard (delivered/opened/clicked)

Multi-tenant impact

Grow+ = bulk campaigns; Starter = 1-to-1 only.

Effort: 45 SP

## Phase 7 — Workflow Automation Engine (4–6 weeks)

Why now: Big-ticket item — powers most of ZNICRM's "automation" sells.

Backend

- WorkflowRule entity (trigger, conditions, actions, enabled)

- Triggers: LeadCreated, LeadStageChanged, DealStageChanged, TaskOverdue, TimeElapsed, IncomingMessage

- Conditions: JSONLogic against the entity (nested AND/OR)

- Actions: SendEmail, SendWhatsApp, CreateTask, AssignTo, MoveStage, Webhook

- Domain event bus (IDomainEventDispatcher) — WorkflowEngine subscribes and matches

- Hangfire delayed jobs for time-based triggers

Frontend

- pages/settings/workflows/ — visual rule builder

- Execution log per rule with replay

Multi-tenant impact

Grow = 10 rules, Scale = 20, Business = 30.

Effort: 60 SP

## Phase 8 — Assignments, Escalations & Approvals (2–3 weeks)

Why now: Built on Phase 7 — specialised action types + UIs.

Backend

- AssignmentRule (round-robin within team, by region, by source, by load)

- EscalationPolicy (if X not done in Y hours, escalate)

- Approval entity (request type, current step, chain, status)

- All three reuse WorkflowRule infrastructure with curated UIs

Frontend

- pages/settings/assignments/, /escalations/, /approvals/

- Approval inbox in user dashboard

Multi-tenant impact

Business+ only.

Effort: 25 SP

## Phase 9 — Cloud Telephony, Call Sync & Dialer (4–6 weeks)

Backend

- TelephonyProvider entity (Twilio / Exotel / Knowlarity / Tata Tele)

- Provider adapters (outbound + recording webhook)

- CallLog entity (linked to customer/lead/deal, direction, duration, recording URL)

- Inbound webhook from each provider

- Click-to-call endpoint

Frontend

- pages/settings/telephony/ — provider config

- In-page softphone widget (WebRTC if available)

- Call log on every customer/lead/deal record

- Recordings inline-player

Multi-tenant impact

Starter = call sync only; Grow = recording visibility; Scale+ = dialer + telephony.

Effort: 50 SP

## Phase 10 — Helpdesk & Knowledge Base (4–5 weeks)

Backend

- Ticket entity (subject, body, status, priority, customer FK, owner, SLA timer)

- TicketComment (public/private replies)

- Email-to-Ticket via IMAP poller (Hangfire)

- KnowledgeArticle entity (title, body, category, public slug)

- Public ticket portal at support.{tenant}.travelcrm.app

- Public KB at help.{tenant}.travelcrm.app

Frontend

- pages/crm/tickets/ — agent inbox

- pages/settings/knowledge-base/ — article CMS

- Public portal sub-app (separate bundle)

Multi-tenant impact

Scale+ only.

Effort: 50 SP

## Phase 11 — Integrations: Webhooks, Zapier, Custom (2–3 weeks)

Backend

- WebhookSubscription entity (events, URL, secret, retry policy)

- Event bus → webhook dispatcher (Hangfire retry queue)

- Zapier integration: triggers + actions exposed via REST for Zapier's app definition

- Generic OAuth2 client registration table for custom integrations

Frontend

- pages/settings/webhooks/ — subscriptions, test fire, recent deliveries

Multi-tenant impact

Grow=5, Scale=10, Business=25 webhooks.

Effort: 20 SP

## Phase 12 — AI Features (5–7 weeks)

Why now: Leverage existing Features/Settings/AiProvider — configs already in place.

Backend

- AiCreditWallet per tenant (token balance, usage log)

- Features/AiAgents/: Followup Intelligence, Deal Revival, Lead Qualifier Bot, AI Reply Suggestions

- All routes through IAiProviderClient abstraction

- Token metering middleware — debit AiCreditWallet

Frontend

- pages/crm/ai-insights/ — Followup Intelligence + Deal Revival dashboards

- Inline AI suggestions in lead/deal/customer detail

- pages/settings/ai/ extended with wallet balance + usage chart

Multi-tenant impact

Scale = Followup Intelligence + Deal Revival; Business = + chatbots + reply suggestions. AI credits sold separately (₹1 = 1 AIC).

Effort: 70 SP

## Phase 13 — Reports & Analytics (3–4 weeks)

Backend

- ReportDefinition entity (filter JSON, columns, schedule)

- Standard reports: Conversion funnel, Source ROI, Sales velocity, Team performance, Pipeline forecast

- CSV/Excel export via EPPlus

- Scheduled email delivery (re-uses Campaign engine)

Frontend

- pages/crm/reports/ — wire up the stub

- ApexCharts dashboards

- Report builder (column picker, filter UI)

- Manager-only team performance views (permission-gated)

Multi-tenant impact

Scale+ for custom reports; standard reports in Starter+.

Effort: 30 SP

## Phase 14 — Polish: Custom Domains, Storage Quotas, Billing UX (2–3 weeks)

Backend

- TenantDomain mapping + Let's Encrypt automation

- Per-tenant storage byte counter (in FileStorage.SaveAsync / DeleteAsync)

- Stripe / Razorpay subscription adapter → TenantSubscription.Status

- Self-serve billing portal endpoints

Frontend

- pages/settings/billing/ — invoices history, payment method, plan upgrade with Stripe Checkout

- Storage usage meter on dashboard

Multi-tenant impact

Business+ unlocks custom domains.

Effort: 25 SP

# 8. Cross-Cutting Concerns

## 8.1 Feature Flags vs Plan Gates vs Tenant Settings

Three distinct concepts — keep them separate:

| Concept | Definition + example |
| --- | --- |
| Plan Feature | Sold per tier — stored in Plan.featureCodes. Example: whatsapp_bulk_campaign |
| Tenant Setting | Configured per tenant — stored in tenant_settings. Example: SMTP host, default currency |
| Feature Flag | Engineering toggle (canary, kill-switch) — config or Unleash. Example: new_pipeline_kanban_v2 |

A user-visible button is shown only if all three conditions are met: plan entitles it, tenant has configured it, feature flag is on.

## 8.2 Plan-Limit Enforcement Pattern

Every Create handler checks the live count against the entitlement before persisting; the Angular service catches "plan_limit_reached:*" errors and shows the upgrade modal.

## 8.3 Data Migration Discipline

- One EF migration per phase, named YYYYMMDD_phaseN_*

- Backfill scripts for existing tenants where a new column needs a default

- Smoke test on a staging tenant before production migration

## 8.4 Security Per Feature

- Lead source webhooks: HMAC signatures per provider

- Public widget endpoints: rate-limit per IP and per publicKey

- Payment gateway webhooks: signed payload verification (Stripe/Razorpay HMAC)

- Custom domains: ownership verification (DNS TXT record check before activation)

- Every new permission added to PermissionCatalog; RolePermissionSeeder grants Admin by default

## 8.5 Observability

- Serilog scope Feature=<code> on each new feature for filtering in Seq

- Hangfire dashboard exposes per-feature job queues

- Prometheus metrics: per-tenant active users, campaign send rate, AI tokens consumed

# 9. Critical Dependencies & Sequencing

- Phase 0 must ship first. Every later phase reads IFeatureGate.

- Phases 1 → 2 → 3 must stay in this order — invoices need customers, customers need deals.

- Phase 7 (Workflow Engine) unblocks Phase 8 and is heavily used by Phases 4, 6, 9, 10, 12.

- Phases 5 (widget), 10 (support portal), 14 (custom domain) all need the same wildcard-cert automation.

- Phase 12 (AI) is parallelisable with everything from Phase 3 onwards.

- Phases 4, 9 are integration-heavy — partner accounts (IndiaMART, FB, Twilio) must be procured before sprint start.

# 10. Risk Register

| Risk | Profile + Mitigation |
| --- | --- |
| WhatsApp template approval delays (Wati / Meta) | Likelihood: High ¦ Impact: Medium — Mitigation: Submit templates 2 weeks before launch; pre-approve fallbacks |
| Telephony provider regional restrictions | Likelihood: Medium ¦ Impact: Medium — Mitigation: Adapter abstraction to swap providers per region |
| AI cost runaway from misbehaving agents | Likelihood: Medium ¦ Impact: High — Mitigation: Per-tenant token cap + circuit breaker + per-feature cap |
| Custom domain SSL automation (LE rate limits) | Likelihood: Medium ¦ Impact: Medium — Mitigation: Use ACME staging in dev; pre-warm certs at provisioning |
| Plan migration of existing tenants | Likelihood: High ¦ Impact: Low — Mitigation: Default existing tenants to 90-day Unlimited trial |
| Perf regression from FeatureGate / global filters | Likelihood: Medium ¦ Impact: High — Mitigation: Cache entitlements per-request; benchmark in CI |
| Workflow rule infinite loops | Likelihood: Medium ¦ Impact: High — Mitigation: Per-event depth limit + circular-dependency check at save |

# 11. Definition of Done (per phase)

A phase is "Done" only when all of:

- All entities have EF migrations + seed data

- All endpoints have FluentValidation + permission attributes + integration tests

- All UI screens are responsive (mobile + dark mode using existing token system)

- Feature is gated by IFeatureGate at the API layer

- Plan-limit counters increment correctly + a "limit reached" upgrade flow exists in UI

- Permission catalog updated; RolePermissionSeeder grants Admin by default

- Hangfire jobs (if any) have a dashboard tag and dead-letter queue

- docs/implemented-modules.docx regenerated to reflect new modules

- Graphify (graphify update .) run to keep the knowledge graph current

- One demo tenant provisioned + smoke-tested by QA

# 12. Open Questions for Stakeholders

- Target market — Indian travel agencies (₹ pricing, IndiaMART/TradeIndia priority) or global (USD, FB/Google priority)?

- Field Force (TeamSpoor) — bundle as a Business-tier feature inside TravelCRMPlus, or keep as a sister product?

- Travel-specific inventory (Hotels/Transport/Activity already built) — extend ZNICRM's generic Products module to merge, or keep them separate?

- AI provider primary — Anthropic only (already configured) or multi-provider routing?

- Mobile app — native iOS+Android, Capacitor wrapper, or web-only?

- Payment gateways — Razorpay (India) + Stripe (global) — both from day one of Phase 14?

- Domain mapping — self-serve in UI, or support-team-assisted for the first 6 months?

This plan is a living document. After Phase 0 ships, refine with actual velocity and re-prioritise against customer feedback.